## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Jhonathan Silva - 23605938
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game board to have a black background
|  | 3 | to control the snake so I can play the game
|  | 4 | to use the arrow keys so I can play with one hand only
|  | 5 | to being able to turn the snake in four directions (left, right, up, down)
|  | 6 | to login so I can play the game
|  | 7 | the snake to eat the prey
|  | 8 | the snake size to increse after eating prey
|  | 9 | pause and resume the game by pressing the Backspace key
|  | 10 | to see my current score based on how many preys the snake ate
|  | 11 | I'd like to record my best score
|  | 12 | I'd like to quit the game using a buttom
|  | 13 | I'd like to have my top score registered even if I quite the game

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Jhonathan Silva -
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard |  | 0% |  |  |  | 95% | 100%
3.1.2 |  |  | GUI for login form |  | 100%
3.2 |  | Build the game logic
3.2.1 |  |  | Login Logic |  | 100%
3.2.2 |  |  | Snake logic |  | 0% | 10% | 20% | 40% | 100%
3.2.3 |  |  | Prey logic |  | 0% | 10% | 40% | 45% | 100%
3.2.4 |  |  | Board logic |  | 0% | 20% | 30% | 45% | 100%
4 | Test and deploy the game |  |  | 3 | 100% |  |  |  |  | 100%
[6 empty] | 40% | 58% | 76% | 100%
5 | Document the game |  |  | 4 | 100% |  |  |  | 100%